## Sayfa1
Recycle IT Task Dependency |  |  | Recycle It Estimates
Work Page | Task | Dependency | Task |  | Optimistic Hour | Realistic Hour | Pessimistic Hour
Preliminary Work | PW1. UI Design |  | Preliminary Work |  | 53 | 67 | 84
Preliminary Work | PW2. Architectureral Design | PW1 | PW1. UI Design |  | 17 | 21 | 25
Preliminary Work | PW3. Technical Documentation | PW2 | PW2. Architectureral Design |  | 20 | 24 | 30
Preliminary Work | PW4. Reserch Analysis | PW3 | PW3. Technical Documentation |  | 4 | 6 | 9
Preliminary Work | PW5. Team Introduction | PW3 | PW4. Reserch Analysis |  | 10 | 13 | 16
Technical Analysis | TA1. Existing Infrastructure Analysis | PW5 | PW5. Team Introduction |  | 2 | 3 | 4
Technical Analysis | TA2. Identify New Infrastructure Needs | PW5 | Technical Analysis Work |  | 5 | 8 | 11
Documentation Analysis | DA1. User's Guide | ND8 | TA1. Existing Infrastructure Analysis |  | 3 | 5 | 7
Documentation Analysis | DA2. Instaliation Guide | ND8 | TA2. Identify New Infrastructure Needs |  | 2 | 3 | 4
Documentation Analysis | DA3. Start-Up Guide | ND8 | Documentation Analysis |  | 11 | 16 | 21
Authentication Tasks | AT1. Sign-In | PW5 | DA1. User's Guide |  | 5 | 7 | 9
Authentication Tasks | AT2. Sign Up | PW5 | DA2. Instaliation Guide |  | 4 | 5 | 6
Authentication Tasks | AT3. Forget Password | AT1 | DA3. Start-Up Guide |  | 2 | 4 | 6
Create Offer Module | CO1. Create Offer Page | BE3 | Dev Work |  | 178 | 221 | 267
Back-End Developer | BE1. Chat Management System | PW5 | AT1. Sign-In |  | 10 | 12 | 15
Back-End Developer | BE2. Payment Management System | PW5 | AT2. Sign Up |  | 11 | 13 | 15
Back-End Developer | BE3. Offer Management System | PW5 | AT3. Forget Password |  | 10 | 12 | 14
Back-End Developer | BE4. User DataBase | PW5 | CO1. Create Offer Page |  | 15 | 18 | 21
Back-End Developer | BE5. Comment DataBase | PW5 | BE1. Chat Management System |  | 10 | 13 | 16
Back-End Developer | BE6. Evaluation DataBase | PW5 | BE2. Payment Management System |  | 12 | 14 | 16
Payment Module | P1. Front-End Developer | BE2 | BE3. Offer Management System |  | 9 | 11 | 13
Chat Module | C1. Front-End Developer | BE1 | BE4. User DataBase |  | 5 | 7 | 9
Other Page Module | OP1. Main Page | PW5 | BE5. Comment DataBase |  | 3 | 5 | 7
Other Page Module | OP2. About Us Page | PW5 | BE6. Evaluation DataBase |  | 5 | 6 | 7
Other Page Module | OP3. Services Page | OP4, OP5, OP6 | P1. Front-End Developer |  | 15 | 17 | 20
Other Page Module | OP4. Food | PW5 | C1. Front-End Developer |  | 10 | 15 | 20
Other Page Module | OP5. Beverages | PW5 | OP1. Main Page |  | 25 | 30 | 35
Other Page Module | OP6. Agriculture | PW5 | OP2. About Us Page |  | 7 | 9 | 11
Other | ND1. PM |  | OP3. Services Page |  | 10 | 12 | 15
Other | ND2. TL |  | OP4. Food |  | 7 | 9 | 11
Other | ND3. Non-Dev | PW5 | OP5. Beverages |  | 7 | 9 | 11
Other | ND4. Planning | PW5 | OP6. Agriculture |  | 7 | 9 | 11
Other | ND5. Functional Test | ND4, AT1 | ND8. DevOps |  | 13 | 17 | 22
Other | ND6. Regression Test | ND5 | Total Work |  | 260 | 329 | 405
Other | ND7. Bug Fix | ND5 | ND1. PM | 0.2 | 52 | 65.8 | 81
Other | ND8. DevOps | PW5 | ND2. TL | 0.2 | 52 | 65.8 | 81
|  |  | ND3. Non-Dev | 0.05 | 13 | 16.45 | 20.25
|  |  | ND4. Planning | 0.1 | 26 | 32.9 | 40.5
|  |  | ND5. Functional Test | 0.2 | 52 | 65.8 | 81
|  |  | ND6. Regression Test | 0.2 | 52 | 65.8 | 81
|  |  | ND7. Bug Fix | 0.25 | 65 | 82.25 | 101.25
|  |  | Grand Total |  | 572 | 723.8 | 891